## BASC Projects
Summary of this sheet | Vivian started this spreadsheet for keeping track of BASC action items and projects. Upto October 2022, all history of the projects had been documented in the monthly meetings and please refer to the monthly meetings for history of these projects and actions. From November 2022 monthly meetings, this will probably be where history is documented
Last updated | 2023-09-02
Project Number/Action Letters | Project Name | POC | Purpose/Main Goal | Status | Start Date | End Date | August 28th | July 24th | June 26th | May 22nd | April 24th, 2023 | March 27th, 2023 | February 27th Meeting | 2023-01-28 | November 23rd 2022 monthly meeting | History of Discussion
Long-term Goal | Update Bike Route (Planning) | David, Vivian, Chad | We will have an updated bike route to plug into the bike plan. | Update | 2022 |  | Bike Route Discussion: (Chad and David): Presented 3 maps of the bike routes. 1) End points 2) Difficulty of bike route roads 3) Close of up of map #2. Alta may ask exactly this information from BASC. David would like to see the difficulty of doing this exercise for all roads of Huntsville. Can a case be made that certain bike routes should be prioritized due to ridership? This map considers the skill level and confidence of bike riders. The map shows that most Huntsville bike routes would not be accessible to most people’s skill level. From Planning it’s possible to overlay bike counts in order to support the claim that certain bike routes should be prioritized. Long-term BASC goal is to print this bike route map to Huntsville, hotels, etc. This would require money and the question is then what grant opportunities for this. Can send out to BASC and BASC Facebook, which will request for other input on this presentation. | Added Chad. Discussed at this meeting. Top 5 Bike Routes Question from Planning→ A separated PPT slide deck was used as a working document and notes.. Vivian sent this to David and Chad, who plan to have a potential map suggest |  | David planning to send video and presentation for BASC June meeting Planning is at the “Scope of Work” stage with updating the Huntsville Bike Plan with Alta. James can send us this information to BASC. This led to a discussion if David Nuttell can present his “Bike every road and updating Bike Route” project at the BASC meeting in June. BASC had questions about the Huntsville Bike plan such as: Does the plan look at sister cities? Yes. Is Bicycle parking in the plan? Will the plan include pedestrians as well? | David has completed and sent to Planning. Can this be a BASC presentation and then in the website? | David Nuttel’s personal map update: Personal project to overlay the missing gaps between the Huntsville Bike Routes and greenways/greenlinks. Given that David has biked EVERY Huntsville city road, he would like to add recommendations for minor changes to routes and stop/yield signs to improve safety and efficiency. BASC discussed that the city’s Planning department may find this helpful because of the Planning group’s pursuit of an updated bike route with the consultant group, ALTA. David will reach out for help from BASC. |  |  | (11/28) Vivian to support new project for a BASC committee: Develop a posted/signed bike network of “Way Finding” with digital QR codes to maps of usable Bike Routes. Use heat maps (STRAVA) and study/overlay Huntsville's GIS map.Vivian reported and showed some STRAVA heat maps overlaying COH GIS Bike Route maps. Noting that many Bike Routes were not used much by cyclists (running Strava). It wasn’t clear if the heavily used (STRAVA indicated) roads were Bike Routes or not. But, it was clear that heat map data could be used to inform Bike Route network design. Jamie mentioned that she had some STRAVA info about some other roads in Huntsville(8/16) Vivian has prepared a presentation to better explain the concept to develop a Cycling Network to support this action (network of “Way Finding” with digital QR codes to maps of usable Bike Routes). BASC to review and answer the questions she has posed. Ask Frances to get us on city council agenda to present a summary. (9/26) No feedback from BASC members yet. Vivian considers this a long-term project. Maybe get “Streetlights data” through HUBS, Peter Hannah might be a resource. (10/5) David is interested in helping but will not be able to until Nov. (10/11) Vivian will need to confirm how this work for this project is related to HSV Planning and understand how it can be integrated because bike routes haven’t been updated since 2006 “MPO bike plan”? And even with a new a bike plan it needs to be integrated into the road design plans of Huntsville. Considerations is that city plans to hire “ALTA Consulting” to support the city’s bike plan. hhh. Action: (10/26) Vivian is following up and will give update Nov. meeting. October: 7. Action: Vivian (cont.) to support new project for a BASC committee: Develop a posted/signed bike network of “Way Finding” with digital QR codes to maps of usable Bike Routes. (10/24) Strava capabilities may be used in 2023 for Bikeways revision. Bike Lane layer versus Bike Routes layer is now on GIS map. Amy is GIS manager. | See October 2022 Monthly Meetings
Report | Greenways | Jo Beth | How is the Greenway system in Huntsville expanding or getting funded | Update |  |  | BASC Letter of Support for Miller Branch Greenway Phase 1 with TAP funding: Approved and sent by Vivian. http://www.huntsvillempo.org/tap/ . General Discussion for the Miller Branch Greenway Phase 1: Where is this Miller Branch Greenway? Search for “Miller Branch Greenway” on this pdf MPO website. Explains briefly that it is a standard greenway design, 12ft asphalt. http://www.huntsvillempo.org/wp-content/uploads/2014/04/bikeped-2.pdf Where does it connect? Singing River Trail, Triana, Madison, Huntsville, Williams Middle school, eventually Wheeler National Wildlife Refuge and Tennessee River. How was this greenway prioritized? A variety of factors. Using the public input responses from the Greenway input sessions from November 2022. It was voted up. Project Readiness such as # of the right of way of property owners and land acquisition required for TAP funding. No ridership data was considered and we currently do not have user data. General Questions to follow-up on: What are the metrics for success for the Miller Greenway? How much does it cost to make a road versus a greenway? Does it decrease car traffic? The TAP does have this language. Traffic Volume is or can be added. In general, prioritization should consider bicycle user because if there are areas where there are more bicycle riders maybe we should prioritize the safe bike infrastructure in those areas with funding. What much does the City spend on bike infrastructure? Where can the public find that data? The only other place Vivian knows of is in the TIP where there is a metric of how many bike lanes were built. | [5 empty] | (3/6) COH Planning conducted the Greenway Master Plan Public Input Workshops at the end of 2022 and is currently compiling all public input. COH Planning is currently working with the Land Trust of North Alabama (LTNA) and the Singing River Trail (SRT) partners to expand the greenway network in the northern and southern portions of the city.
C | Event | Dario | Dario Send pedicab contacts to Larry | Old | 2022-10-01 | [9 empty] | 11/28: not discussed | See October 2022 Monthly Meetings
D | Vision Zero | Larry | Larry will send a Vision Zero Action plan to Dario | Old | 2022-10-01 | [9 empty] | 11/28: not discussed
2021 Goal | Add Sidewalks on Oakwood East of Parkway (TE) | Jamie | Sidewalks on either side of Oakwood east of the Parkway. Jamie is working on a proposal to document the needed improvements to Oakwood Ave, possibly for a future DOT/MPO Active Transportation grant. | No update | 2021 |  |  |  | Email Correspondence June 11th. with Presentation | [5 empty] | Frances updated saying Jim McGuffey (COH Dept of Urban Development) is getting involved with the property on Oakwood and KiLeddare. | See October 2022 Monthly Meetings
2023 Goal | Crash Analysis Studio - Strong Towns | Larry, Dario, Danny | Deep dive into Bike Fatality with Strong town methods This is an example of a Strong Towns Crash Analysis Stuido: https://www.strongtowns.org/crash-studio | No update |  |  |  |  | Vivian asked for volunteers at BASC June monthly meeting. Larry has been working with Dario, Danny, Vivian, and Strong towns. Will do traffic counts, gathering about 2 hours of data.. Look at real speed. Take an hour to do the analysis. Included now Morgan, Austin, Jo Beth (cc’ed), James Vandiver (cc’ed). Notes about the area: Will be part of the transit study in the next 4-5 years. Mile west of university has a raised median. Lights do not illuminate the westbound lanes. Streets blog. Has studied it too. 35 mph even at high peds. Action: Larry and Vivian started an email chain for those interested in this project and will be setting a meeting at the end of July to continue. Vivian needs to include Jacob Hell and follow-up if James Vandiver is another contact. | May 31st- Larry received data package requirements and shared to BASC email, expected to complete by July, and scheduled for a zoom call with Strong towns in September. They need volunteers to get the data. | bike fatality on June 7th, 2021: Josh Gurley on Univerisity https://www.rocketcitynow.com/article/news/local/cyclist-killed-on-university-drive-identified-coroner-huntsville/525-ee040c8f-2f44-4c72-9908-c6d4e347675f#:~:text=HUNTSVILLE%2C%20Ala.,%2Dyear%2Dold%20Joshua%20Gurley. https://whnt.com/news/huntsville/coroner-identifies-bicyclist-killed-in-crash-on-university-drive/
Report | Official HPD Bike/ped Police- reported incidents | Anthony, Dario | Important to allow BASC to analyze the bike/ped incidents and how biking can be improved because BASC has a variety of biking experience in Huntsville. This report would come from the HPD police reporting system, which is only visible for HPD. | No update | pre-2022 |  |  |  | Update: Anthony was able to get a HPD report from TE. These reports can tell us what happened in these bike incidents. The updates for the reports that were asked about on the BASC June Agenda are added below. The report given can be used from 2015 and seen for each year. Information may need to be redacted such as victim and offender. This report will be used in parallel with CoH Vision Zero. Update by Larry is that Dario was able to pay for a specific police report for $25. So there is a public process to get police reports process but it costs money. | Dario plans to reach out to the Police Precinct to get a report. Larry suggested asking Capt. Mike Izzo: https://www.huntsvilleal.gov/residents/public-safety/huntsville-police/police-operations/administration/ | Anthony’s update about Hobbs Island Road/Ditto’s landing bike crash (4/10) : Truck versus bicycle and bicycle victim is a priority 3 (the lowest severity). So due to priority, HPD didn’t send a homicide guy to the scene. So Anthony needs to figure out how to find the ticket incident #? Unfortunately, the new HPD system didn’t allow officier to see the traffic incident # when the call was made. Instead it is generated to your computer and data goes to the state. Jaime reiterated and BASC expressed interest that this data used to come to BASC monthly to analyze. |  | The question will continued to be asked because this data was something that BASC had looked at in the past. The discussion was that this data may still be maintained by Traffic Engineering, Tom Cisco. Action: Anthony plans to follow-up with Tom. | Due to privacy, Anthony can only give us basic information about these incidents at the BASC meetings. Follow-up with HPD if there are any new incidents since the latest BASC meeting. Anthony re-iterated that if there is a case that if you feel like you have been endangered by an aggressive driver in Huntsville that you can contact your police precinct. Vivian has found further instructions on how to file a criminal police report with HPD on the See and Be Seen Huntsville website that also lists Police Precincts: https://www.bikehuntsville.com/bike-huntsville/make-a-report-or-request/
2021 Goal | Revise 2015 Crash Data Report (HPD) | Dario, Jamie, Vivian, Danny | Dario is working on a draft report on crash data from 2015 to present. | No update | 2021 |  |  |  |  | For educational purposes and awareness: Added this to BASC Facebook and hsvbasc.com --> Minutes and Documents --> BASC Projects --> Crash data folder Not closed because action items from April 2023: 2) Send to Huntsville VisionZero Task force. Present this at Vision Zero at the kick-off to initiate discussion. Government’s duty is to put the infrastructure in. Needs to be more than BASC to see and understand this analysis. This is a model advisory role. 3) Can this be added to “Seeandbeseen.com”? Ask Kelly. | Dario’s Crash Data Report: Notes and discussion points in April 24th BASC meeting miutes, but refer to slides for main points and recommendations. BASC actions: 1) Crash Analysis presentation is on the hsvbasc.com for educational purposes: All voted yes, no objections. Posted here: hsvbasc.com --> Minutes and Documents --> BASC Projects --> Crash data folder 2) Send to Huntsville VisionZero Task force. Present this at Vision Zero at the kick-off to initiate discussion. Government’s duty is to put the infrastructure in. Needs to be more than BASC to see and understand this analysis. This is a model advisory role. 3) Can this be added to “Seeandbeseen.com”? Ask Kelly. | Dario had given a brief overview of his analysis on the Huntsville Bike/Ped Crash data that used pedbikeinfo.org, ALDOT, and additional information that Jo Beth provided at the last presentation in 2022. This analysis would be able to suppor the city's Multimodal Safety Action plan. Action: BASC to review presentation and provide comments/questions by April 11th. One comment was to add sources to each of the slides. At the April BASC meeting, BASC will vote as a BASC supported crash report and to vote to where this presentation is to be forwarded. BASC voting members list is in the hsvbasc.com --> Minutes and Documents folder. |  |  | (10/24) Dario made his presentation to BASC at October monthly meeting. Lots of discussion. Data is presented, but hard to draw conclusions. Dario is still to produce a map of fatalities. BASC to give feedback. Jo Beth sent email of crash data information from the planning group, email [BASC] Monday, Oct 24 BASC Meeting 5:30 pm STA | See Project folder and October 2022 Monthly Meetings
2021 Goal | Planning See and be seen website and see click fix recommendation | James, Danny | James Moore will update the SeeandBeSeen site in order to have this website provide public link and update verbiage to say that. | No update | 2021 |  |  |  |  | BASC reaching out to suggest how can BASC update the SeeandBeSeen website with SeeClickFix reference Community Events BASC educational information |  |  | See the Reports named "Planning SeeClickFix.com report a"nd "See and Be Seen Reporting tool " |  | (11/28) Not working correctly. Currently doesn’t provide confirmation after a report is submitted. (identified potential contacts in the COH Communications group to address)Kelly Schrimsher is the decision maker, Lucy Du berry (sp?) does social media. Jacob Hell in ITS? BASC Recommendation: Pursue SeeClickFix.com to see if a new category could be added for “Traffic/Transportation Issues”. This category would provide reports for Planning (BASC Planning action, James Moore, to ask what this might look like) and BASC citizens discussed action of making "near-miss" SeeClickFix tickets on https://seeclickfix.com/huntsville as an "Other" category (similar to what was described on see and be seen https://www.bikehuntsville.com/bike-huntsville/make-a-report-or-request/). (Vivian plans to try this action and email BASC of results.) | See October 2022 Monthly Meetings
Long-term Goal | Bike Lane Sweeping | Danny | Get bike lanes prioritized as a regularly scheduled road maintanence | No update | [5 empty] | Which bike routes have regularly scheduled sweeping? Cecil Ashburn is regularly scheduled because of its design. It is possible that the City has stopped doing regularly scheduled but instead do these by request. Danny plans to reach out to Landscape based on the policy. Can marked bike lanes be prioritized? Can this go to Vision Zero Plan?
2023 Goals | Bylaw review | Danny, Vivian, Chad, Larry | Review BASC laws. Recommended every 5 years. | No update | 2023-01-01 | [8 empty] | Discussed and added as a 2023 BASC goal at January BASC monthly meeting. Latest Review was 11/2022
2023 Goals | Host a Map-a-Thon |  | BASC and HUBS to support an in-person mapathon by the end of the year for Peopleforbikes.org This goal will support the other goal of Huntsville becoming a bike friendly city status with League of American Cyslists | No Update | 2023-01-01 | [7 empty] | David Nuttal should be added. Bruce knows bike rack. Explain History added here:This goal was brought up last minute in 2022 and HUBS and BASC members were only able to do individual updates to the open source map. Hosting a marathon guideline is referenced by people for bikes: https://cityratings.peopleforbikes.org/about/contribute?eid=126577 This will help with bike friendly city statis | This goal was brought up last minute in 2022 and HUBS and BASC members were only able to do individual updates to the open source map. Hosting a mapthon guideline is referenced by people for bikes: https://cityratings.peopleforbikes.org/about/contribute?eid=126577
2023 Goals | Support the renewal of Bike Friendly status of HSV businesses Bicyclists | Jamie | BASC to support the renewal process for the Bike Friendly status that are given to businesses to the League of American Bicyclists group. Getting more bike friendly businesses may allow those businesses to get more recognition and to get more bike racks to their business. More info. https://www.bikeleague.org/business | No Update | 2023-01-01 | [7 empty] | Added Jamie. Larry has a name on Facebook that they might be interested in helping out with this goal. Needs to find the name. | This was brought up because STA is a bike friendly business which may need help for the renewal project. Another bike friendly busniess is Bicycle Cove. Gold Sprint would be a good new candidate to support. This award can be expanded to bike friendly communities and universities. Reference this list here: https://www.bikeleague.org/bfa/awards
2023 Goals | Bike to school: Chapman School | Jacob, Chad, Jamie, Anthony | Once Oakwood bike lanes are installed, want to plan a bike to school day to Chapman school with parents and kids | No Update | 2023-01-01 |  |  |  |  | Might be interested in the first week in October Jacob gave an update on how the Chapman school event went (Lynn is the POC). Event consisted of kids bringing their own wheeled transportation to ride on the track at the school. HUBS Coop provided some bikes that were used for the event, then distributed to kids | Chapman: Jacob updated BASC that Chapman will do a “Cruisin’ into the Summer'' event, which are kids riding around Chapman. There wasn’t enough lead time and maybe experience to bike bus (4-5 volunteers) or a bike to school day event this year, but Chapman is interested. CoH communicated through the superintendent who communicates to the school that Bike to School day was May 3rd. HUBS let Chapman borrow bikes (5/5)- Jacob's note in discord | Jacob spoke with Lynn. Lynn, Julia, and parents will coordinate further. There are no plans or logistics on a planned bike ride to Chapman at this time. Note May 24th is the last day of school. Another idea was School streets for Autumn timeframe: https://nacto.org/publication/streets-for-pandemic-response-recovery/emerging-street-strategies/school-streets/ | Jacob: He has some interested folks. Julia Kirckoff/Lynn from the school is interested. Anthony is interested. Recommended to get the PTA involved. | Discussed and added as a 2023 BASC goal at January BASC monthly meeting. (2/1) Jacob has gotten into contact with parents around Chapman and has gotten some contact.
2023 Goals | Encourage bike to work week and Mayor's bike ride | BASC citizens | Encourage bicycle safety awareness from BASC during May bike Month, Bike to work week, and to any Huntsville communications (flyers, etc). BASC to be at Mayor's Bike ride and have HSV communications to note that on. Goal to have something by bike month which is May. | No Update | 2023-01-01 |  |  |  |  | Completed and presented to BASC May meeting, but BASC Timeline should be updated and add number of people who showed up to this event Note in the minutes is that: One of the biggest Mayor’s ride events was held at Campus 805 and so for future planning this might a spot to consider to increase participation. | BASC put up flyers BASC and HUBS supported Mayor's bike ride with bike raffle and post-ride Ride to the Salty Nut. BASC planned and promoted on BASC Facebook every week in May for Bike Month BASC wrote, reached out, and recorded with WLRH Next year? Close streets for bikes downtown and neighborhood part? | At the BASC meeting, BASC discussed all the April and May bike events that are listed in the March monthly minutes, Section 1. This list will be communicated out on the BASC Facebook and hopefully the city's See and Be Seen website https://www.bikehuntsville.com/ , which is updated by the city's communication group. Action: Anyone can lead a bike ride to work the week of May 15th-21st, just encouraged to post your bike ride on social media like Facebook. Mayor's bike Ride Section: BASC dispensed Mayor's Bike Ride vendor forms to bike shops by deadline of April 1st. Action: BASC will be provided with City Flyers to post around the city, such as bike shops and where BASC members find fit. Jamie's Pro-tip: get two flyers and tape them back to back. Then hang up on the inside window of the shop, allowing people to see the flyer from both side. Action:Jamie would like to make an announcement on WLRH about bike month. Waiting on the City's Flyer to communicate coordinated information and give people a single source reference. Action: HUBS will have a bike raffle for one adult and one kid bike during Mayor's bike ride event. The winner will be announced about half an hour when the bike ride is finished. Bruce supports a bike ride after the Mayor's a bike ride by having the Salty Nut Open earlier (~11am) TBD. Action: Vivian will follow-up with Bruce to confirm Mayor's bike ride time. From vendor's form, even begins at 10:30am and end at 12:30pm. Action: BASC would like to plan to lead a bike ride from the Mayor's Bike ride to the Salty Nut Brewery afterwards. | Planning says that Mayor's bike ride is scheduled May 6th and after that announcement of the free transit would be made which is May 8th through the 12th. Offline discussions with Kelly are still being made to confirm the Mayor's ride date. Jamie’s update on bike to work Month: Jamie would like to start a group bike ride to work onto the Arsenal in May. Jamie wants to work with the city to get this communicated out more. Potential dates discussed May 15th-21st. on to the Arsenal as groups. Vivian added this to 2023 BASC goal “ Encourage bike to work week and Myor’s bike ride” Which date would work best for Jamie and then BASC can then communicate to the city? MWR pass needed. Gate 10 opens March 6th Jamie has an update about the Tour d’Arsenal. Reached out to the Garrison about Tour d’ Arsenal about starting this up again. It’s really cool annual ride that was held prior to COVID. Tour d’Arsenal: https://www.bikehuntsville.com/bike-huntsville/riding-in/on-the-arsenal/ | Need to contact Kelly Schrimsher and Lucy Berry DeButy from HSV Communications group. Reference to COH website: https://www.huntsvilleal.gov/government/departments/communication/ 2022 Mayor's Bike ride from the Huntsville Blast website: https://hvilleblast.com/3-things-you-need-to-know-about-road-biking-in-huntsville/
2023 Goals | Free Transit ride if you bring your bike | James, Danny | Reach out to City to give citizens a free bus ride if they bring their bike. | No Update | 2023-01-01 |  |  |  |  | What are the numbers? Morgan has seen more bikes and buses | BASC promoted on BASC Facebook. COH Facebook promoted: https://www.huntsvilleal.gov/huntsville-bicyclists-invited-to-try-transit-for-free-this-week/?fbclid=IwAR2SHLFCP4B8PenPrCGGeR0HJeWTPG_-g-V-MtNkclI6zz17cjXNOIR-6k0 Note other place that this was promoted: https://patch.com/alabama/huntsville/try-transit-offering-free-bikes-rides-city-employee-indicted | Huntsville Transit will provide Free rides if you bring a bike to the bus from May 8th-12th. | Danny reached out to John, but we got it from James at the meeting that John Autry approved of a Free Transit if you bring a bike from May 8th-12th. | James brought this idea up and referenced someone from the city would be excited to do this (I don't remember which person that was Jim?) Discussed that this could be around bike to work week, May 15th-21st, bike to work day is May 19th. This is the COH website that is about transit and could be used as a contact person: https://www.huntsvilleal.gov/residents/streets/public-transportation/
2023 Goals | Support Tour-de-ville Kids event or have a booth | Larry, Jamie, Anthony | BASC to support Tour-de-Ville with a kids Traffic gardent event. 2022, BASC and city planning attended Tour-de-Ville with posters and flyers to talk to the community about bike safety and city planning. | No Update | 2023-01-01 |  |  |  |  | Anthony/Jaime interested in doing a safety class at Tour de Ville. Is there enough people? HUBS is advertising a lot and giving bikes away. |  |  | added Larry as POC. From last meeting: Maybe we can target the Boy and Girl Scouts of Huntsville as a community who would be interested in this event. | Jamie and Anthony may have experience of doing this 2 years ago. Maybe we can target the Boy and Girl Scouts of Huntsville as a community who would be interested in this event.
Grant | Land and water Conservation Fund (LWCF)/Reacreational Trails Program (RTP) A&M Greenway | Jo Beth | Grant to make "A&M Greenway" | No Update | 2023-01-01 | [7 empty] | (3/6) COH Planning is currently developing a proposal for the “A&M Greenway” segment running along the NARM RR ROW. Planners/LTNA conducted a site visit and discovered that due to site constraints and a narrow ROW, we would have to build on the adjacent A&M property, and is currently in communication with A&M regarding the project. If given the “OK” form A&M, Planning to pursue either LWCF or RTP funding for the 1.1-mile project. | Need to follow-up with Jo Beth for what the other grant was.
Grant | Bloomberg Initiative for Cycling Infrastructure (BICI) | Jo Beth | to improve bike & pedestrian safety and connectivity into the Downtown area and environs. | No Update | 2022 | [7 empty] | (3/6) The Planning Department is currently working on a Downtown Active Transportation Connectivity Action Plan (Plan sent to BASC for review) to improve bike & pedestrian safety and connectivity into the Downtown area and environs. Planning just submitted a Bloomberg Initiative for Cycling Infrastructure (BICI) grant application for the project. This is global competition, and only 10 cities will be awarded. Awards announced in “Spring 2023.” | Jo Beth 1. Bloomberg grant is being worked. "Bicyce" grant. $1M for bike infrastructure 2. LCWCS application, they are looking at the railroad behind A/M (Email Jo Beth) (1/30) Email Downtown Active Transportation Plan and BICI funding opp
Grant | USDOT SMART Planning & Prototyping Grant | Jo Beth/Jennifer | To fund the testing of the new smart traffic light technology, Mio Vision, for traffic, including bike/ped safety. | No Update | 2022-11-01 |  |  | Discussed at this meeting. See minutes for discussion. Greenways: Grants, we have the TAP (transportation alternative. program) and is identifying greenway and sidewalks projects for the TAP. Updated the TAP applications and posted on MPO site→ Vivian tried to find but could not find and can follow-up at next meeting. We have money to work with it for TA projects ($4 mil) Suggestions? Hobbs road to green cove was approved? Just submitted the Safe streets for all grant (Holmes). Need VisionZero plan → which CoH has started. VisionZero this Wednesday, 12:30pm. Tons of grant after this the SS4A grant includes grants to fund: SMART signal for Bob Wallace, phase 1 is pilot demonstration. USDOT (reconnecting communities (PARC bridge), looking for additional funding,--> can it be used for landscaping along Pinhook Creek before the bridge? Aand neighborhood access grant for BARGE projects for this intersection at Memorial Parkway has 2 pots of money: http://www.huntsvillempo.org/plans-and-reports/ |  |  |  |  | (3/6) COH Planning is currently working with Traffic Engineering and a vendor on a USDOT SMART Planning & Prototyping Grant to test new smart traffic signal technology for multimodal safety and congestion & emissions reduction along Bob Wallace Avenue to see if it can be implemented city-wide. (SMART grant awards have not been announced yet). | No update. Mio Vision uses cameras with specific discernment capabilities to count different types of traffic, like bicycles, pedestrians, cars SUVs, light trucks specific large trucks, semis. If TE, is awarded the 3-5 year grant to be awarded later in 2023, they plan a pilot program along Bob Wallace Avenue to see if it can be implemented city-wide. For more info--> https://miovision.co Follow up occasionally, should be awarded 2023.
Grant | USDOT funding for Holmes Ave. Complete Streets | Jo Beth | Funding for Holmes Avenue Complete Streets Corridor Project. | No Update | 2022-11-01 |  |  | Discussed at this meeting. See minutes for discussion. Greenways: Grants, we have the TAP (transportation alternative. program) and is identifying greenway and sidewalks projects for the TAP. Updated the TAP applications and posted on MPO site→ Vivian tried to find but could not find and can follow-up at next meeting. We have money to work with it for TA projects ($4 mil) Suggestions? Hobbs road to green cove was approved? Just submitted the Safe streets for all grant (Holmes). Need VisionZero plan → which CoH has started. VisionZero this Wednesday, 12:30pm. Tons of grant after this the SS4A grant includes grants to fund: SMART signal for Bob Wallace, phase 1 is pilot demonstration. USDOT (reconnecting communities (PARC bridge), looking for additional funding,--> can it be used for landscaping along Pinhook Creek before the bridge? Aand neighborhood access grant for BARGE projects for this intersection at Memorial Parkway has 2 pots of money: http://www.huntsvillempo.org/plans-and-reports/ |  |  | VisionZero had a good turnout, well received, and well publicized. Media may not have gotten the VisionZero information until the last minute (internal technical reasons). Surveys and crash analysis are being looked at by Planning now. Task Force has 21 people and will have focus groups with 5 areas. Monthly meetings during lunch and will have a kick-off to introduce initial findings. VisionZero Survey is open until May 10th, which means it was available for 1 month. The hope was to put bike information on “Seeandbeseen.com” website (Kelly (Director)/Adam Smith (Transportation)). | (3/27) BASC recommended 3 candidates to the city's Vision Zero Task force and will support the City's Vision Zero Planning effort of a Multimodal Safety Action Plan. | (3/13) BASC recommended 3 candidates for consideration to the Safety Action Plan Task Force after obtaining a quorum of Citizen voting members. (Huntsville Vision Zero Municipal Safety Action Plan) (3/6)COH Planning is continuing to seek USDOT funding for the construction of the Holmes Avenue Complete Streets Corridor Project. (The project was not awarded the USDOT Safe Streets For All (SS4A) grant/but we are embarking on a city-wide Vision Zero Safety Action Plan to increase our chances for a Construction grant for this year’s round. (More on this effort below!) This includes embaring on a Municipal Safety Action Plan in 2023.
Grant | RAISE for the sky bridge | Jo Beth | Funding for the Pedestrian Access Redevelopment Corridor (PARC) Project, a multimodal improvement project that includes a bike and pedestrian bridge that will span from the Mill Creek/Lowe Mill neighborhoods into Downtown. | No Update | 2022-11-01 |  |  | Discussed at this meeting. See minutes for discussion. Greenways: Grants, we have the TAP (transportation alternative. program) and is identifying greenway and sidewalks projects for the TAP. Updated the TAP applications and posted on MPO site→ Vivian tried to find but could not find and can follow-up at next meeting. We have money to work with it for TA projects ($4 mil) Suggestions? Hobbs road to green cove was approved? Just submitted the Safe streets for all grant (Holmes). Need VisionZero plan → which CoH has started. VisionZero this Wednesday, 12:30pm. Tons of grant after this the SS4A grant includes grants to fund: SMART signal for Bob Wallace, phase 1 is pilot demonstration. USDOT (reconnecting communities (PARC bridge), looking for additional funding,--> can it be used for landscaping along Pinhook Creek before the bridge? Aand neighborhood access grant for BARGE projects for this intersection at Memorial Parkway has 2 pots of money: http://www.huntsvillempo.org/plans-and-reports/ |  |  |  |  | (3/6) In 2022, the City was awarded $20,000,000 in transportation funding through the USDOT Rebuilding American Infrastructure with Sustainability and Equity (RAISE) Discretionary Grants Program for the Pedestrian Access Redevelopment Corridor (PARC) Project, a multimodal improvement project that includes a bike and pedestrian bridge that will span from the Mill Creek/Lowe Mill neighborhoods into Downtown. **The City is continuing to pursue additional funding for the PARC project through the Bipartisan Infrastructure Law (BIL) programs. (We applied for a USDOT ReConnecting Communities grant, but it was not awarded. We intend on continuing to pursue additional funding for the project).
Long-term Goal | BASC reach out to ALDOT |  | Bike routes go beyond city limits which is why reaching out to the state may be needed. | No Update | [5 empty] | Discussion: Can BASC reach out to ALDOT in order to get them involved with road concerns in Huntsville? Can BASC identify a POC at ALDOT? This stem from a SeeClickFix ticket that David submitted a Huntsville SeeClickFix ticket, who then directed him to use the ALDOT road concern equivalent because it is a state road. https://cpmsapps2.dot.state.al.us/RoadConcerns/?fbclid=IwAR1rLqFTTkSmk25dpab7KSTTJ_mQZEvJkIBRKDCWBNcxBO4VU20xcM1p-bo Bike routes go beyond city limits which is why reaching out to the state may be needed.
Long-term Goal | Create Safe Routes to School (SR2S) (HPD) | Anthony | Make a Safe Routes to School (SR2S) events at the schools | No Update | 2021 | [9 empty] | Safe Routes to School (SR2S) ideas to be prepared for schools and principals. We need to put together info and a “Plan” for a May 2023 event. The Nat’l SRTS Org has lots of material: https://www.saferoutesinfo.org/ Must find a way to get it to all principals and see if some are interested. Get the material approved by the COH Superintendent or school board. Will contact “Rocket City Mom”, Stephanie Walker. Anthony thinks Blossomwood would be a good place to do a SRTS program. Ben Payment forwarded School board contacts. (9/26) Anthony really wants to do bike safety skills class at schools as the promotion for fall SRTS event. Anthony gave the update that they were able to train 20 new bike cops this month and that there are 6 bike cops now at UAH. Anthony gave a brief discussion of how they train cops, going up and down stairs, mountain bikes, can citizens do a class like this with cops? Action: (9/26)Dario sending email to Anthony and school board/superintendent. Vivian will make a new project based on Anthony’s interest in making a safety skill class. And will add a new “Monthly topic”. Vivian wants to make a video of the class or some sort of safety skills class. | See October 2022 Monthly Meetings
Long-term Goal | Update Huntsville Municipal Code (Planning) | Ben | Update Huntsville Municipal Code regarding multimodal connectivity for the new Greenway Plan. | No Update | 2021 | [9 empty] | Ben Payment emailed this report: Ben spoke with Planning (Dennis Madsen) and Engineering (Shane Davis) and speaking for BASC, proposed 3 main areas of improvements to the Huntsville Municipal Code regarding multimodal connectivity. 2 areas are addressed in the new Greenway Plan. Complete streets part is addressed in the comprehensive planning along “Holmes Corridor”… thru UAH and then on to Madison Pike to Madison Blvd. Ben attended a Stakeholder Meeting on Holmes Corridor. Grant still in process. Letter of support needed from BASC. (9/26)Vivian and Jamie wrote a BASC letter and sent to Jo Beth 8/26 email “Letter of Support for SS4A grant to fund Holmes Ave. Corridor Project”. pp. | See October 2022 Monthly Meetings
Long-term Goal | Make BASC an official city committee (Citizens) | Larry | Make BASC an official committee, like MPO CAC or MPO TCC | No Update | 2021 | [9 empty] | (11/28) Discussed the pros/cons of making BASC official. Currently, BASC does not have the manpower to pursue this project. Here lists the pros/cons: | See October 2022 Monthly Meetings
Long-term Goal | Can there be an option to take a bike skills training course instead of a drivers test if you get a traffic ticket? |  |  | No Update
Long-term Goal | BASC or HPD bike skills training course |  | Bike safety skills training course lead by League of American Bicyclists instructors or HPD? | No update | [6 empty] | Vision Zero HPD project- Go to the high schools to teach biking. Every high school has a bike patrol officer. HPD has asked the question since HPD teaches DUI, what to do at traffic stops, at the schools, can they teach about bike on the 1 day. Vision Zero- Elizabeth Flemings- school contact who could connect with HPD. Can BASC be seen the bike curriculum? Anthony and Jamie.>> Make a action category
Report | Lost Bikes | Anthony | To know if and how citizens can report lost bikes from HPD and get their lost bikes back | No update | 2023-01-01 | [8 empty] | New: Anthony explained how there are two groups of lost bikes that are processed at HPD so citizens can contact HPD more. In general, the recommendation is to write down your bike’s serial number and your name in the handlebar so that when you need to confirm that that is your bike, you can access it there, where most people do not look. HUBS wants to work with HPD as well as create a HUBS lost bike process using (https://bikeindex.org/ Larry wants to follow-up with Anthony on HUBS bike registry.
Report | Planning SeeClickFix.com report | James | Would allow citizens to submit a “Bike” related category and possibly “near-miss” incidents onto SeeClicFix, which could then be sent directly to the COH Planning dept. This is important because this is a public website supported by the city, citizens use this website, and tickets can be routed directly to the correct city group.This can be used to see the increase of biking interest in Huntsville. https://seeclickfix.com/huntsville | No Update | 2022-11-01 | [7 empty] | Discussion: There are some SeeClickFix.com tickets that go to Planning currently. Sidewalk repairs go to Planning. BASC wants to know what categories go to Planning and who categories these tickets. Assumption is an IT group. Another question is if HPD gets SeeClickFix.com , Anthony does not know. People in the city who might know the answers are Chris McNeese (COH PUblic Works- General Servies) and Tara Sloan as seen in this article: https://cityblog.huntsvilleal.gov/huntsville-connect-customer-service-app/ Action: I think James will follow-up with some personnel listed. BASC members can try to track their tickets to see if sidewalk repair tickets go to Planning and track where their "Other" tickets go to. | James to work within the Planning team to see if this category is an option. TE has commented that in their group and their category (Traffic Signal, Traffic/Street Sign), SeeClickFix cannot be used for capital projects; but instead, only as a tool that citizens can report road “signage” issues. See example of a ticket that is being worked by TE: https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/13935917?fbclid=IwAR20ZwsAYTEfYDRLzrHTDMzRnoQq00MPcXA-Cm7n_-D0ITypCjQjUqdIPOk Vivian will note that this question of a separate category for Planning/bike lanes is supported by this ticket where someone tried to request bike infrastructure on seeclickfix.com and Planning’s Alternative Mode Report : https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/map/11477966?lat=34.72380992161543&lng=-86.5832169612525&max_lat=34.73969862815559&max_lng=-86.55060129963145&min_lat=34.70791816084959&min_lng=-86.61583262287355&search=%2011477966&status=open%2Cacknowledged%2Cclosed%2Carchived&zoom=14 Alternative mode report pg 2: https://www.huntsvilleal.gov/wp-content/uploads/2020/04/FINAL-2020-Alternative-Modes-Review.pdf | (11/23) BASC Recommendation: Pursue SeeClickFix.com to see if a new category could be added for “Traffic/Transportation Issues”. This category would provide reports for Planning (BASC Planning action, James Moore, to ask what this might look like) and BASC citizens discussed action of making "near-miss" SeeClickFix tickets on https://seeclickfix.com/huntsville as an "Other" category (similar to what was described on see and be seen https://www.bikehuntsville.com/bike-huntsville/make-a-report-or-request/).
Report | See and Be Seen Reporting tool | James/ Jo Beth | Allows the City to count-up The number of bike “near-miss” incidents and website views. This can be used to view the increase of biking interest and “near-miss” incidents in Huntsville. https://www.bikehuntsville.com/bike-huntsville/make-a-report-or-request/ | No Update | pre-2022 | [5 empty] | Danny is planning a BASC action to request from COH communications if BASC can update the Seeandbeseen.com website to post these monthly topics. | Reiterated that the See and Be Seen Huntsville website is still online and being operated by the city's Communications group. Only the Reporting tool on this website is not working and is showing a 404 error. BASC is recommending and actively suggesting a workaround. https://www.bikehuntsville.com/ | (3/6)Substitute for See & Be Seen: Planning currently in discussions w/BASC and Comms regarding substitute for the See & Be Seen Reporting Tool, and actively looking into alternatives. (we hope this will get more attention/clarity as we move forward with our safety action planning effort).. Planning said that the See and Be Seen "near-miss" reporting tool is difficult to maintain by the city and so it is currently obsolete, currently showing Error 404 page. The question is what is the workaround, possibly from SeeClickFix.com. SeeClickFix.com isn't used for this and most-likely not a valuable workaround. Action: BASC (Danny and other interested people) will escalate offline in order to make sure that citizens have a place to record these near-misses because this is valuable data. | The reporting tool continues to not work since 2021. Planning has tried to update for the past year (2022). See error: https://www.bikehuntsville.com/bike-huntsville/make-a-report-or-request/ The POC for this website is the COH Communications group:https://www.huntsvilleal.gov/government/departments/communication/ Escalate: Danny and Planning will email Kelly Schrimsher and Lucy Berry DeButy | (11/23) Not working correctly. Currently doesn’t provide confirmation after a report is submitted. (identified potential contacts in the COH Communications group to address)Kelly Schrimsher is the decision maker, Lucy Du berry (sp?) does social media. Jacob Hell in ITS? | See October 2022 monthly meetings
Report | MioVision Report Traffic Engineering | Jennifer | Potential report of new data traffic camera, MioVision | No update | 2022-11-01 | [9 empty] | TE and Planning worked on a USDOT SMART Planning & Prototyping Grant to fund the testing of the new smart traffic light technology, Mio Vision, for traffic, including bike/ped safety. Mio Vision uses cameras with specific discernment capabilities to count different types of traffic, like bicycles, pedestrians, cars SUVs, light trucks specific large trucks, semis. If TE, is awarded the 3-5 year grant to be awarded later in 2023, they plan a pilot program along Bob Wallace Avenue to see if it can be implemented city-wide. For more info--> https://miovision.com/ BASC is excited!
Report | Bike signals Report | Jennifer/Gordan | Can bike count data can be collected and reviewed by BASC based on the number of times the spragins bicycle signals are triggered? No, don't have the technology at this time (2023). This also applies to other bike specific road signals (specific road sensors, oblong diamonds, which can supposedly differentiate might have data as well?) | No update | 2023-01-01 | [6 empty] | Update on if a bike report can be generated from triggered bicycle signals at Spragins and 5 points intersection? TE does not have COM (recording capabilities) at this time, but can be capability later. There was some discussion of how the loop detection works. There could be issues with the loop detection due to weight or conductive material of the bike. | Update on if a bike report can be generated from triggered bicycle signals at Spraggins (and others)? TE does not have COM (recording capabilities) at this time, but can be capability later. Loops are only vehicle detection (object detection) and cannot tell the difference between bikes and cars. Gordan would be the POC for traffic signals and explain more about this. Action: Jennifer was going to follow-up on the question about the Spragins bike signal (the push button) and the 5 points intersection (Leddar signal). Basically if these two specific sections can detect bicycles then a bicycle report. Spragins because it is a bike push button signal, I believe. 5 points because cyclists are able to be detected really really well there, possibly using Leddar detection. | Vivian emailed TE 1/16 and it should be routed to Gordan. Follow-up with Gordan by the next BASC meeting.
Report | Annual Alternate Modes Report | Jo Beth | Annual report made by the COH Planning department that reports the progress of the walkability and bikeability of the city | No Update | pre-2022 | [8 empty] | Not discussed at this meeting, but note that 2020 is the only accessible report. https://www.huntsvilleal.gov/wp-content/uploads/2020/04/FINAL-2020-Alternative-Modes-Review.pdf The city posted the 2021, but it doesn’t work right now. Have not found 2022. BASC will need to follow-up from this article https://cityblog.huntsvilleal.gov/what-to-know-about-alternative-modes-planning-in-huntsville/
Report | Zoning | Jo Beth | How is Zoning considering alternative mode infrastructure | No Update | [8 empty] | (3/6) COH Planning is currently working on a Zoning Ordinance Update which takes into consideration alternative mode infrastructure.
Report | Environmental Sustainability Committee (HESC) | Jo Beth | How is Planning and HESC working together | No Update | [8 empty] | (3/6) COH Planning is currently working with multiple stakeholders on the Huntsville Environmental Sustainability Committee (HESC) to draft sustainability initiatives for the city, including a work group dedicated to sustainable transportation alternatives.
Report | Other Bike/Ped Police incidents | Anthony, Vivian | This report was created because Anthony from HPD mentioned that he keeps an eye out on Facebook, news articles, BASC email and if he knows the issue/concerns, he can follow-up. | No Update | 2023-01-01 |  |  |  |  | Created Tab in this spreadsheet "Crash Incidents for HPD" in order to list incidents that the public sees other than through HPD. |  |  |  | New: HPD cannot give out information about biking/ped police reports that readily due to privacy… But Anthony keeps an eye on Facebook and says that if he knows the situation through Facebook (he is on the BASC email list too), then he can create a case for us and follow-up. Vivian created a HPD report in the Excel spreadsheet. Follow-up with HPD if there are any new incidents since the latest BASC meeting.
Report | Traffic Engineering SeeClickFix.com report | Jennifer | Can TE generate a report for BASC to analyze bike-related seeclickfix.com tickets that went to Traffic Engineering, from Category called “Traffic/Street Sign” https://seeclickfix.com/huntsville | No Update | 2022-11-01 |  |  |  |  | TE does the same filtering as the public. The process is noted in the "SeeClickFix" tab of this Excel sheet | See Monthly minutes: Tom Cisco is TE analyst for the crash data analysis, posted to a website (traffic counts on the city’s GIS gov. website). Planning is talking to him about publishing the crash data. Planning want by June/July is to get the GIS map to make interactive. Jaime confirms that the city has been doing this in the past. BASC request is to get monthly crash data, which is what BASC used to do. The BASC suggestion is that if Tom needs support to make the data readable, then BASC could support. Jo Beth and Dario can follow-up. Open SeeClickFix tickets: TE has been finding out. 5-6 tickets should be addressed in the next few days. Basically, roads were resurfaced so bike detections painting had to be added again. Bike signals will be rechecked or bike signal paintings will be added in the next couple of days. TE note to BASC is to call TE directly if bikes are not being detected by traffic light (sometimes it’s the bike), call main Traffic Engineering number/ Jim Rogers (main SeeClickFix.com). If it is a traffic signal not detecting then calling would allow them to get through it quicker and also if this is a recurring issue for certain traffic lights, calling would escalate the issue because the detection loop might need to be fixed. This can be added as BASC protocol, but follow-up question by Vivian. If called-in, can Jim make a ticket on SeeClickFix.com in order to track the progress? Spragins ticket, bike lane: TE has had consistent issues getting the bikes to be detected at the loop. So the TE recommendation is going to adjust the wave tronic. If this ticket is closed, just call TE because they might have to replace something if it continues to |  |  | Update: Jennifer says that a report is not generated on their end. The only possible way to filter is the same as if citizens can do it. BASC to figure out a workaround, consider filtering themselves or continue keeping up through discussions/emails in the BASC group by the next BASC meeting. | Discussion at the meeting was how TE receives the SeeClickFix tickets. (BASC TE action) Ask Jim Rogers, a TE admin guy, if a report can be generated, esp. bike/ped related to have at BASC monthly meetings
Report | Bike Parking/Signage Enforcement | Planning | Bike infrastruction such as bike racks be added to property (city, businesses, etc) is needed in order to make it more accessible to use bicycles as a form of transportation (just like cars as a mode of transportation) Huntsville has a policy regarding bicycle parking: https://library.municode.com/al/huntsville/codes/code_of_ordinances?nodeId=COOR_APXAZOOR_ART76BIPARE | No Update | [5 empty] | Added the "Bike Racks" tab to make list of ongoing questions | BASC email correspondence to city was made to continue the pressure onto adding bike racks to businesses (May 3rd) BASC can support to install bike racks. Did city provide a timeline? | (4/7) Planning, 8 racks to be provided for Lincoln Mill. It's part of parking improvements. C.O. includes walk thru by City departments. Subway across the street also doesn't have bike racks and needs to comply prior to C.O. Redstone banking downtown doesn't hace bike racks. City looking into it. (3/30) Ben Payment contact by email to city TE and Planning about Lincoln Mill's bike parking situation. Should have bike parking according to city policy. Action: City to provide timeline
2 | Drake and Hastings (TE) | Jennifer | Will look into a better/possible solution for safer conditions for Cyclists where the long-time bike route crosses Drake at Hastings. | Closed | 2021 | October monthly meeting | [8 empty] | Jennifer Colee has replaced Gordon as the TE rep to BASC. Discussion with Jennifer is that she mentioned a hawk signal nor a pedestrian island would not be possible because of the proximity to the major intersection at Whitesburg and drake. I think TE’s general POV is there are some areas that should not be crossed. However, citizens POV is that there are people who cross there and they need some security. Discussion about how pedestrians will cross where most convenient to get to destination because walking takes a long time and more effort physically. (10/24) Closed. No room for median. Can’t put a x-walk or flashing hawk. Possible to replace with LED flashing sign. TE is not interested in discussing. | See October 2022 Monthly Meetings
6 | BASC to recommend NACTO for TE (Citizens) | Larry | Larry will provide a letter from BASC to recommend the COH join NACTO for a year to learn the benefits. | Closed | 2021 | November monthly meeting | [8 empty] | (11/28) Larry contacted NACTO and TE and we got back the answer that TE is not interested in becoming a paying NACTO member. Email 10/25: [BASC] NACTO member cities | See October 2022 Monthly Meetings
Community concerns | Bradford road | BASC citizens | Concerns about Bradford as described on SeeClickFix ticket #13935917: :https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/13935917?fbclid=IwAR20ZwsAYTEfYDRLzrHTDMzRnoQq00MPcXA-Cm7n_-D0ITypCjQjUqdIPOk | Closed | 2023-01-01 | [6 empty] | Voted to close at March BASC meeting | Vivian will post on FB how this looks now with video for closure. SeeClickFix ticket :https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/13935917?fbclid=IwAR20ZwsAYTEfYDRLzrHTDMzRnoQq00MPcXA-Cm7n_-D0ITypCjQjUqdIPOk Additional comments on BASC Facebook (1/13/2023):https://www.facebook.com/groups/1366468327053612 | Bruce discussed with Nick about a bike lane to separate bikes and cars as it preferred, but cannot be done. TE plans to sign and paint, further Vivian to Follow-up on this ticket: :https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/13935917?fbclid=IwAR20ZwsAYTEfYDRLzrHTDMzRnoQq00MPcXA-Cm7n_-D0ITypCjQjUqdIPOk Additional comments on BASC Facebook (1/13/2023):https://www.facebook.com/groups/1366468327053612
Community concerns | Oakwood bike lanes | BASC citizens | This was a planned road diet and installation of bike lane. Citizens had concerns that the current repaving (BASC email: Repaving of Oakwood with the addition of bicycle lanes) Reference to BigPicture Huntsville: https://bigpicturehuntsville.com/places/five-points-northeast-huntsville-small-area-plan/ | Closed | 2023-01-01 |  |  |  |  | Closed | Oakwood bike lanes have been striped. See monthly minutes | Bike Lanes is the plan (still), Public Works is the lead but communicates with TE because TE makes the design. Public Works does resurfacing contracts specifically. BASC will continue to ask questions through TE. | Chad (3/8) Bike Lanes on Oakwood: stripes for the bike lanes painted on Oakwood. No markers (i.e. signs that say bike lanes or painted bikes on the road) at that time. Striping on Oakwood: The center has been done. So it will be done soon. Publix Works is the group working on this. | It will take 2-3 weeks due to asphalt standards. TE said that they will do an analysis of the road which will be reported around the summertime. Follow-up in the summer. If possible, BASC members/citizens let people know when this bike lane is completed on social media or email so that the community knows that this has been completed. Danny to follow-up on a bike lane infrastructure idea where tire bumps lines the bike lanes so if a cars swerves in then they will be alerted or rumble strip along the bike lane. | It will take 2-3 weeks due to asphalt standards. TE said that they will be bike lanes and do a study. Groove payment, and tire. https://bigpicturehuntsville.com/places/five-points-northeast-huntsville-small-area-plan/

## See Click Fix tickets
A process for bike-related SeeClickFix tickets
1 | Create Bike Signal/Sign related tickets through See Click Fix Huntsville. Below are examples of bike-related SeeClickFix tickets. If there are ones that did not work as intended, bring it up to the next BASC meeting during Section I | https://seeclickfix.com/huntsville
2 | Call Huntsville Traffic Engineering to get a faster response. Note that this might be only followed-up by email or phone and you cannot view this on SeeClickFix (currently 6/2) | https://www.huntsvilleal.gov/government/departments/traffic-engineering-department/
3 | How to search for any "bike" related tickets on See Click Fix? Use Keywords such as bike, biking, cycling, | Home page-->map/list (half screen)--> Filter button | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/list?lat=34.71349034016042&lng=-86.67115364223572&max_lat=34.826299153281646&max_lng=-86.50670204311484&min_lat=34.60052744494172&min_lng=-86.83560524135662&search=bike&zoom=11
https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/map?lat=34.723809921616024&lng=-86.58321696125397&max_lat=34.73791769320169&max_lng=-86.56266051136387&min_lat=34.70969974216878&min_lng=-86.60377341114408&search=bike&status=open%2Cacknowledged%2Cclosed%2Carchived&zoom=14
4 | State road issues may be directed to ALDOT's road issues website (see the next link) from SeeClickfix | https://cpmsapps2.dot.state.al.us/RoadConcerns/?fbclid=IwAR1rLqFTTkSmk25dpab7KSTTJ_mQZEvJkIBRKDCWBNcxBO4VU20xcM1p-bo
Last updated | 2023-11-01 |  |  |  | 964
Requestor | Main Concern | SeeClickFix Category | Area | Status | Ticket Number | Comments | Links
Jamie | Debris in multi-use path | Curbside Debris Collection | Research Park | Acknowledged | # 13381414 |  | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/13381414
Jim | Bike Signal | Traffic/Street Sign | West Central | Acknowledged | # 13354073 |  | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/13354073
Vivian | Bike Signal: Oldmadison/bridgestreet | Traffic/Street Sign | Research Park | Acknowledged | # 12770576 |  | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/12770576
Vivian | Bike Signal | Traffic/Street Sign | West Central | Acknowledged | # 13024127 |  | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/13024127
Vivian | Bike Route 60: Bradford drive | Traffic/Street Sign | Research Park | Acknowledged | # 13935917 | Vivian plans to make video! See BASC Feb. minutes | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/map/13935917?lat=34.72885868013269&lng=-86.6731159845577&max_lat=34.73077427527586&max_lng=-86.6690390268554&min_lat=34.72694304059392&min_lng=-86.67719294226&zoom=17
George | Bike Racks | Other | Downtown | Archived | # 9487352 |  | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/9487352
Unknown | Bike lane should be included | Other | Downtown | Archived | # 11477966 | This is an example of how tickets are diverted automatically | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/map/11477966?lat=34.72380992161543&lng=-86.5832169612525&max_lat=34.73969862815559&max_lng=-86.55060129963145&min_lat=34.70791816084959&min_lng=-86.61583262287355&search=%2011477966&status=open%2Cacknowledged%2Cclosed%2Carchived&zoom=14
Vivian | Crosswalk | Traffic/Street Sign | Research Park | Archived | # 12778905 |  | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/12778905
Vivian | Crosswalk: : Enterprise/University Place | Traffic/Street Sign | Research Park | Archived | # 12779420 | Still have concerns | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/12779420
Vivian | Bike Signal | Traffic/Street Sign | West Central | Archived | # 12817614 |  | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/12817614
Vivian | Greenway | Park Maintenance | South Huntsville | Archived | # 12817804 |  | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/12817804
Vivian | Tall bushes | High Grass/Weeds | Research Park | Archived | #13502546 |  | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/complete/13502546
Vivian | Bike lane debris | Curbside Debris Collection | Martin Road | Archived | # 13509045 |  | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/13509045
Anonymous | Bike Signal | Bike Signal/Scale | Monroe/Williams | Closed | # 14059210 | BASC Feb meeting: this was closed quick | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/14059210
Anonymous | Bike Signal | Bike Signal/Scale | Governors Dr Sw & Seminole Dr | Closed | # 14059240 | BASC Feb meeting: this was closed quick | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/14059240
Anonymous | Bike Signal | Bike Signal/Scale | Holmes Ave./Andrew Jackson | Acknowledged | # 14071476 | BASC Feb/ meeting: Last one, Leddar, wait until a bike person signal is painted on the road. | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/14071476
Jenn | Pedestrian crossing |  | Pegasus Dr Huntsville, AL, |  | # 13676202 | Detailed response that says why TE declines to add a crosswalk at this point. | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/13676202
Anonymous | Pedestrian crossing | [5 empty] | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/complete/14134686?duplicate=false
Anonymous | Blind Curve |  | Edworth Dr. |  | # 14142324 | Was there a response? | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/14142324
Anonymous | Crosswalk |  | Wellman and Russell |  | # 14160408 | Thank you for contacting City of Huntsville, Traffic Engineering. We do not install crosswalks unless a sidewalk and a curb are present. If you would like to talk with the City Planning Department about having a sidewalk and curb installed here, you may contact them at 256-427-5100. | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/complete/14160408?duplicate=false
Anonymous | Crosswalk |  | Wellman and Andrew Jackson |  | # 14160410 |  | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/complete/14160410?duplicate=false
Anonymous | Sidewalk Repair |  | Andrew Jackson Way Ne & Pratt Ave |  | # 14160461 | The provided link discusses the evaluation process and a list of roadways that have been approved: https://www.huntsvilleal.gov/residents/streets/repaving/. If you have additional questions, please call Huntsville Public Works at 256-883-3944. | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/complete/14160461?duplicate=false
Tris Wilson | Traffic/Street Sign |  | Putman/72 intersection |  | #13900975 |  | https://seeclickfix.com/issues/13900975-traffic-signal
Anonymous | Traffic/Street Sign |  | Russell |  | # 14160475 |  | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/complete/14160475?duplicate=false
Anonymous | Traffic Signal | Bike Signal/Scale | Meridian/Pratt (northbound) |  | # 14228588 |  | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/complete/14228588?duplicate=false
Anonymous | Needs a speed limit |  |  |  | # 14266744 | The Huntsville Fire Department has deemed Epworth Dr a primary response route for fire and EMS calls and therefore, is ineligible for traffic calming. The radar speed sign on Epworth Drive was installed on 6/4/2020 at the request of a citizen due to a speeding complaint and the street being ineligible for traffic calming. The Traffic Engineering Department uses our radar feedback signs as educational tools for residents and users of subdivision streets when that street is ineligible for traffic calming. With over 3,000 municipal streets and several dozen requests for traffic calming each year, these signs are moved around to different streets across the City to help educate and mitigate traffic complaints related to speeding. The Huntsville Police Department also has similar signs for use and can be contacted for speeding issues. The North Precinct Community Relations Officers would be the point of contact at 256-746-4100. | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/14266744
Anonymous | bicycle signal | Spragins |  |  | # 14271864 |  | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/14271864
Jim | Pedestrian Signal | Governors/Seminole |  |  | # 14283946 |  | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/14283946
CoH | Curbside Debris Collection |  |  |  | # 14570443 |  | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/14570443
Ben P. | Bicycle Sensor | Diamond/Old Madison Pike |  |  | # 14874073 |  | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/14874073
Anonymous | Pedestrian Signal | Diamond/Old Madison Pike | Closed |  | # 14987844 |  | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/14987844
Anonymous | Meridian Street- debris and class | Downtown/Dallas | Closed |  | #15508829 |  | https://seeclickfix.com/issues/15508829
Vtrip | Gap between sidewalk and road | Governor's/Harvard | Acknowledged |  | # 15397961 | Formerly 15530479, escalated to admin since this was originally rejected because of "ALDOT" | https://seeclickfix.com/web_portal/536ne61tUkLvo5MSUWwKfSZY/issues/map/15397961?lat=34.71977215222519&lng=-86.57601085264089&max_lat=34.72738220234779&max_lng=-86.5597030218299&min_lat=34.71216140163154&min_lng=-86.59231868345186&status=open%2Cacknowledged%2Cclosed%2Carchived&zoom=15

## Crash Incidents for HPD
Last updated | 2023-09-18
BASC meeting asked | Date Resolved | Topic | Notes
2023-05-01 |  | Pedestrian killed by car | Pedestrian killed by car:: Wall Traiana Hwy/Cleghorn Blvd, May 4th 2023, at 4:30am: https://www.waff.com/2023/05/04/pedestrian-hit-killed-by-car-wall-triana-hwy/
2023-04-01 |  | Hobbs Island truck vs. bike | Any further updates on Hobbs Island truck vs. bike https://whnt.com/news/huntsville/one-transported-to-hospital-after-wreck-involving-bicycle-and-vehicle/
2023-06-01 |  | Memorial Parkway/Mastin Lake commercial truck vs. bike | June 7th: https://whnt.com/news/huntsville/bicyclist-critically-injured-in-crash-with-commercial-vehicle/ https://www.waaytv.com/news/concrete-truck-hits-bicyclist-on-memorial-parkway-in-huntsville/article_b4cc7068-0565-11ee-8293-ef44dba0c41b.html
2023-06-01 |  | First degree assault due to running over a woman exercising on a bike | https://www.al.com/news/2023/06/madison-county-authorities-seek-man-they-say-ran-over-woman-on-bicycle.html https://www.facebook.com/mcsosheriffAL/posts/pfbid02ocZPp978pppicwXkA3wCc6fCRWJgWQnGEYsp2qkUFTzNQUR6a1hKaeK7nXMrm1THl https://www.waff.com/video/2023/06/23/neighbors-madison-co-speak-out-after-woman-was-run-over-while-exercise-bike/
2023-08-01 |  | Ped hit and killed on University Drive near Shogun to Jordan Lane | Was this a hit and run? https://www.waff.com/2023/08/05/pedestrian-killed-after-being-hit-by-vehicle-university-drive/?fbclid=IwAR3b89xBx8ydhFV3qsxj7hvroCzQso55H1dIZKYt4yeZc1qmn5K5nUL02bs
2023-09-01 |  | Motorcycle and Cyclist University Drive at Hillview drive near Jordan Lane | https://whnt.com/news/huntsville/two-seriously-injured-after-motorcycle-vs-bike-crash-on-university-dr-road-closed/?fbclid=IwAR2X8691vVk1u4uDJ-Sp5uLZ0vJBxar18QB3aP8eoDSdgPBXuIXbo4N-rEc

## Bike Racks
Potentially coming

## Road paving
Potentially coming